Program Name:  African American HIV/AIDS Initiative                    	           RFP#: DDP-611K-45414-12-HPACC

| Goal: Decrease HIV transmission among gay men in Virginia Beach by providing comprehensive risk counseling and services to MSM with repeat STDs in the past 12 months. | Measures of Success – Met all staffing needs, all partners are in-serviced, the advisory board is established and active, appropriately trained health educator and outreach workers, and evaluation tools and measures are in place and on file. Notify all health initiative cooperatives of CRCS and enrollment criteria. Outcome Evaluation Questions – Has appropriate infrastructure been established, health initiatives have been notified, screening, and enrollment of 15 MSM? |  |  |  |
| --- | --- | --- | --- | --- |
| Objective 1 | Activities | Data/Evaluation | Timeframe for Assessing Progress | Team Members Responsible |
| Objective 1: Enroll 15 high-risk MSM in Comprehensive Risk Counseling and Services (CRCS) by the end of the first quarter. | 1-1. Hire and train CRCS social workers by January 30. 1- 2: Advertise CRCS services and criteria for enrollment through health departments, drug treatment centers, and CBOs by February 15. 1-3: Complete the development of screening criteria and assessment tools by February 28. 1-4: Screen and enroll 15 MSM referred for services by collaborating agencies. | 1-1: Employee and administrative assistant files 1-2: Distribution material and relationships established with health initiatives. 1-3: Evaluation Forms/Tools 1-4: Registration forms completed, communication established. | 1-1: 1/30/11 1-2: Ongoing 1:3: 2/28/11 1-4: 3/31/11 | 1-1: Executive Director, Program Coordinator, Health Educator 1-2: Program Coordinator/Health Educator, 100 Black Men, AME Ministers 1-3: Executive Director, Program Coordinator, Health Educator 1-4: Health Educator and Program Coordinator |

| Goal: Decrease HIV transmission among gay men in Virginia Beach by providing comprehensive risk counseling and services to MSM with repeat STDs in the past 12 months. | Measures of Success – CRCS participants will complete all contracts, risk assessments, and action plans. All client files contain referral forms, risk assessments, and action plans. $10 gift certificates are available for each session. Complete and fulfill goal plans and risk assessments before discharge. Outcome Evaluation Questions – Are CRCS participant’s contracts, risk assessments, and action plans completed and signed? Is the phone log available to confirm staff has reminded participants of appointments? Is the referral form in the client file? If the client is ready to be discharged, have their goals been achieved? |  |  |  |
| --- | --- | --- | --- | --- |
| Objective 2 | Activities | Data Evaluation | Timeframe for Assessing Progress | Team Members Responsible |
| OBJECTIVE 2: Provide 6-10 sessions of CRCS for each enrolled client by the end of 2010. | 2-1: Enrolled clients will be asked to sign a contract for CRCS participation. 2-2: Complete Personalized risk assessments. 2-3: Develop individual action plans with each client based on the risk assessment and client needs. 2-4: The CRCS social workers will phone clients to remind them of appointments. 2-5: Refer participants to the appropriate mental health, housing, substance abuse treatment, and other services. 2-6: Provide $10 gift certificate to participants will for each completed session. 2-7: Discharge participants from the program after the achievement of goals. Complete a personalized risk assessment. | 2-1: Contracts Signed 2-2: Risk assessments on file 2-3: Submitted action plans mandated to accompany risk assessment 2-4: Complete phone logs and client list before scheduling appointments 2-5: Client file will have a referral form for completion, if necessary. 2-6: Gift certificates available for each session 2-7: Completed discharge and risk assessment in client file | 2-1: 3/31/11 2-2: 3/31/11 2-3: 3/31/11 2-4: Ongoing 2-5: Ongoing, as necessary 2-6: Monthly 2-7: 12/31/11 | 2-1: Program Coordinator, Health Educator 2-2: Program Coordinator, Health Educator, Outreach Workers 2-3: Program Coordinator, Health Educator, Outreach 2-4: Health Educator, Program Coordinator 2-5: Executive Director, Program Coordinator 2-6: Health Educator, Outreach Worker 2-7: Executive Director, Program Coordinator, Health Educator |

| Goal: Decrease HIV transmission among gay men in Virginia Beach by providing comprehensive risk counseling and services to MSM with repeat STDs in the past 12 months. | Measures of Success – Contact and schedule clients who have completed the required sessions for three months follow up. Return client’s files now contain a final risk assessment for comparison. Return client files contain signed gift certificate receipt. Outcome Evaluation Questions – Has the return clients been contacted three months after program completion? Have they been scheduled for a return visit? Is there a completed comparison risk assessment and signed gift card receipt on file for the return client? |  |  |  |
| --- | --- | --- | --- | --- |
| Objectives 3 | Activities | Data Evaluation | Timeframe for Assessing Progress | Team Members Responsible |
| Objective 3: Following discharge from CRCS, conduct a three-month follow-up assessment with clients to determine the maintenance of risk-reduction behaviors. | 3-1: Contact clients by phone and mail to meet for a three-month follow-up. 3-2: Complete a risk assessment and compare results to the previous assessments. 3-3: Provide clients with a $20 gift certificate for completing the follow-up. | 3-1: Phone log and appointment scheduled. 3-2: Risk assessment completed in client file. 3-3: Client file contains signed gift certificate receipt form | 3-1: Ongoing 3-2: Ongoing 3-3: Ongoing | 3-1: Health Educator, Outreach Workers, 3-2: Program Coordinator, Health Educator, Outreach Workers 3-3: Program Coordinator, Health Educator, Outreach Workers |

Outcome Objective 1: By the end of 2010, 80% of clients who complete CRCS will report a reduction in the frequency of unprotected sexual activity as measured by the risk assessment questionnaire.

Outcome Objective 2: By the end of 2010, 60% of clients who reported a reduction in unprotected sexual activity will still be engaging in protective behaviors three months following discharge as measured by the risk assessment questionnaire.

BROADENING PERSPECTIVES – AFRICAN AMERICAN FAITH INITIATIVE: HIV STIGMA REDUCTION AND HIV PREVENTION (RFP#: DDP-611K-45414-12-HPACC)

Dr. KEYONDA SMITH

PROGRAM EXECUTIVE DIRECTOR

SEPTEMBER 02, 2016

PERFORMING ORGANIZATION:
Roane Medical Institute

Richmond, VA

NON TECHNICAL SUMMARY: Despite overall advances in medical care and treatment, African Americans with HIV in the United States have higher mortality rates than whites, a medical fact especially significant in Virginia, which has one of the fastest-growing HIV incidence rates in the country. Whether due to lack of education, cultural views, or personal beliefs, information about safer sex, HIV/AIDS, and related stigmas are not reaching the African American community.

Participants in the first-year HIV prevention intervention are expected to show an increase in their use of condoms during sexual intercourse and the utilization of HIV and sexually transmitted disease (STD) counseling, testing, and treatment services.

OBJECTIVES: Increase the percentage of all ethnic/racial minorities who, if infected, are aware of their HIV infection, with a focus on African Americans. Increase the percentage of all MSM who, if infected, are aware of their HIV infection. Among men who have sex with men (MSM), increase the proportion who consistently engage in behaviors that reduce the risk for acquisition of HIV. Improve access to voluntary, client-centered counseling and testing (VCT) in high seroprevalence communities and populations at risk, focusing mainly on populations with high rates of undiagnosed infection. Monitor behaviors, including behaviors that increase the risk of HIV infection (among persons who are HIV-uninfected) and behaviors that increase the risk of HIV transmission and the risk of disease progression (for persons who are living with HIV); and provide locally relevant data for community planning.

APPROACH: Outreach Initiative will target:

- Congregations and/or their clergy: a local grouping of believers (such as a church) that meets on a regular (usually weekly) basis

- Religious coordinating bodies (RCBs): intermediary organizations responsible for coordinating and supporting congregations

- Nongovernmental organizations: faith-based NGOs employ staff, receive external donor support, and are answerable to a broader group than a  congregation or RCB

- Community-based organizations (CBOs): local groups differentiated from NGOs because they do not employ full-time staff

PROCESS: Outlined in the attached Work Plan.